# Checkpoint Meeting Minutes
## Group Identifier:
9

## Date of Meeting:
24	01	2017

## Attendance Register:
Name	Present
Jackson	X
Joshua	X
Athanasios	X
David A	X
David C	X

If present mark with (X), approved absence (A), otherwise leave blank

## Progress review of last week

Name	Task Description	Task Status
Jackson	Set up folders with git and netbeans	C
Person 1	Create Class diagram for module	C
Person 1	Set up database	O
Joshua	Set up folders with git and netbeans	C
Person 2	Create Class diagram for module	C
Person 2	Start programming authentication	O
Athanasios	Set up folders with git and netbeans	C
Person 3	Create Class diagram for module	C
Person 3	Start programming authentication	O
David A	Set up folders with git and netbeans	C
Person 4	Create Class diagram for module	C
Person 4	Start programming authentication	O
David C	Set up folders with git and netbeans	C
Person 5	Create Class diagram for module	C
Person 5	Start programming authentication	O
Person 6
Person 6
Person 6

Max three rows per group member. Task status: (C) completed (O) ongoing (X) no report
## Plan for next week

Name	Task Description	Task Status
Jackson	Fix database	O
Person 1	Start programming parts	N
Person 1
Joshua	Start programming authentication	O
Person 2	Start programming vehicle	N
Person 2
Athanasios	Finalize class diagram	O
Person 3	Start programming customer	N
Person 3	Design template for GUI	N
David A	Look at java FX / start GUI for authentication	N
Person 4	Start programming bookings	N
Person 4
David C	Start programming authentication	O
Person 5	Start programming specialist repairs	N
Person 5
Person 6
Person 6
Person 6

Max three rows per group member. Task status: (N) new (O) ongoing (X) no report

## Other Issues and Risks
We are unsure about how integrating all he modules will work, once we have a better idea about how our own modules will work we will clarify ambiguities and re-review the integrated class diagram.